## Shared_Parameters
Shared Parameter Name | Shared Parameter Group | Parameter Type | Parameter Group | Instance
4D_Task_ID | 4D Modelling | Text | Identity Data | TRUE
Construction_Zone | 4D Modelling | Text | Identity Data | TRUE
Classification_Uniclass_Description | 4D Modelling | Text | Identity Data | TRUE
Classification_Uniclass_No | 4D Modelling | Text | Identity Data | TRUE

## Construction_Seq
Uniclass_Descrip | Uniclass_Code | Sequencing Order | Production Rate in Hrs | Production Rate in Days | Rate Unit
Concrete columns | Pr_20_85_16_15 | 07 | 0.5 | 0.020833 | item
Carbon steel columns | Pr_20_85_16_11 | 08 | 0.5 | 0.020833 | item
Concrete beams | Pr_20_85_08_15 | 03 | 1 | 0.041667 | item
Carbon steel beams | Pr_20_85_08_11 | 04 | 0.5 | 0.020833 | item
Carbon steel trusses | Pr_20_85_90_13 | 05 | 0.5 | 0.020833 | item
Flat roofs | EF_30_10_30 | 10 | 0.5 | 0.020833 | square metre
Concrete piles | Pr_20_85_62_18 | 01 | 1 | 0.041667 | cubic metre
Concrete pile caps | Pr_20_85_62_19 | 02 | 0.5 | 0.020833 | cubic metre
Walls | EF_25_10 | 09 | 0.5 | 0.020833 | cubic metre
Concrete solid slabs | Pr_20_85_14_16 | 06 | 0.5 | 0.020833 | square metre

## Zone_Seq
Construction Zones | Sequencing Order
Note on B2: Mark McDaid: User to populate sequence order (in form 00)

## Level_Seq
Levels in Model | Sequencing Order
Note on B2: Mark McDaid: User to populate sequence order (in form 00)

## Generated_Schedule
4D_Task_ID | Name | Code | No.of items | m3 | m2 | Duration | ID | Predecessors